- A Sample Residential Construction Schedule - (for a 6,000 square foot custom home) - Is the Microsoft Project template file used to create this new house construction schedule for sale? Yes, a number of professional custom homebuilders and residential project managers have asked to buy the Microsoft Project file that was used to create the new house construction schedule shown on this page. In response to these requests, we are providing sample construction scheduling files for you to review so that you can determine if your residential construction company might benefit from using a scheduling program to help manage your home building business. - [ download sample files ] How long does it take to build a house? Scroll down this page to see an example of a typical construction schedule for a large custom home. It was produced using Microsoft Project® scheduling software and includes most, but not all, of the activities involved in the process of building a new house in Maryland. Sample construction draws have been included for reference purposes, although individual lenders & mortgage companies will most likely have their own draw schedules. Notice that because construction draws from the lender typically follow the completion of various phases, or milestones, the cash flow on a project can be very irregular. While the money flowing out of a construction company; for employee salaries, benefits, office space, vehicles, insurance, equipment and other company expenses, typically occurs on a regular calendar based timeline, the money used to pay these expenses follows an event driven schedule. Therefore, besides the "normal" unplanned events that can affect the progress of a home building project, it is not uncommon for home builders to rearrange construction schedules in order to gain access to draw money so that they are able to pay subcontractors and suppliers in a timely manner. By the way, this is generally a good thing (provided you have an honest builder) because subcontractors tend to follow the money and happy subs are almost always preferable to unhappy ones:-) - Will your house take this long to build? Probably not; most home building projects will take less time, but some will take even more. For example, the timeline for a smaller house, with few options and less detailed finishes, which has been built many times before by professional builders, might be as short as 8 to 12 weeks. However, 6 to 9 months from start to finish is probably a more realistic average (average is not a good word for a typical homeowner). While a larger house, with more options, custom features, fancier finishes, and more owner involvement - especially if the owner has little construction experience - may very well take 1 1/2 to 2 years to complete. Then again, if you build your own house, and make the common mistake of moving in before every last detail is finished, well, you might be looking at decades instead of months or years — I speak from experience, but it's just a little trim in the powder room, and a short piece of baseboard behind the master bath door, and a small piece of molding in the hallway linen closet, and.... The actual schedule of completion for your specific project will vary based upon many factors including, but not limited to, size and degree of difficulty of the structure, site and weather conditions, material and contractor availability, crew sizes, effective scheduling and communication, the knowledge and experience of those managing the project, and perhaps most significantly, the number, timeliness, and complexity of the changes you will inevitably make to the original contract after construction has already begun. Good luck with your project, thank you for visiting B4UBUILD.COM, and have fun building!

|  | ID; Outline Number; Name; Duration; Predecessors; Start; Finish. 1; 1; Contracts; 0.00d; .; Thu 6/5/14; Thu 6/5/14. 2; 1.1; - Supply Lot Sale Agreement; 0.00d; .; Thu 6/5/14; Thu 6/5/14. 3; 1.2; - Supply Construction Agreement; 0.00d; .; Thu 6/5/14; Thu 6/5/14. 4; 1.3; - Supply Contract Plans; 0.00d; 3; Thu 6/5/14; Thu 6/5/14. 5; 1.4; - Supply Contract Specifications; 0.00d; 3; Thu 6/5/14; Thu 6/5/14. 6; 1.5; - Supply Contract Site Plan; 0.00d; 3; Thu 6/5/14; Thu 6/5/14. 7; 1.6; - Secure Financing; 0.00d; .; Thu 6/5/14; Thu 6/5/14. 8; 1.7; - Construction Loan Settlement; 0.00d; .; Thu 6/5/14; Thu 6/5/14. 9; 2; Document Review & Revision; 25.00d; .; Thu 6/5/14; Wed 7/9/14. 10; 2.1; - Review & Finalize Plans; 15.00d; 4; Thu 6/5/14; Wed 6/25/14. 11; 2.2; - Review & Finalize Specifications; 20.00d; 5; Thu 6/5/14; Wed 7/2/14. 12; 2.3; - Review & Finalize Site Plan; 1.00d; 6,10; Thu 6/26/14; Thu 6/26/14. 13; 2.4; - Print Construction Drawings; 5.00d; 10,11,12; Thu 7/3/14; Wed 7/9/14. 14; 2.5; - Approve Revised Plans; 0.00d; 13; Wed 7/9/14; Wed 7/9/14. 15; 2.6; - Approve Revised Specifications; 0.00d; 13; Wed 7/9/14; Wed 7/9/14. 16; 2.7; - Approve Revised Site Plan; 0.00d; 13; Wed 7/9/14; Wed 7/9/14. 17; 3; Bids & Contracts; 24.00d; .; Thu 7/10/14; Tue 8/12/14. 18; 3.1; - Make Copies of Plans; 3.00d; 14; Thu 7/10/14; Mon 7/14/14. 19; 3.2; - Make Copies of Specifications; 2.00d; 15; Thu 7/10/14; Fri 7/11/14. 20; 3.3; - Distribute Plans & Specifications; 1.00d; 18,19; Tue 7/15/14; Tue 7/15/14. 21; 3.4; - Receive Bids; 10.00d; 20; Wed 7/16/14; Tue 7/29/14. 22; 3.5; Review Bids; 5.00d; .; Wed 7/30/14; Tue 8/5/14. 25; 3.6; - Execute Subcontractor Agreements; 5.00d; 23; Wed 8/6/14; Tue 8/12/14. 26; 4; Grading & Building Permits; 17.00d; .; Thu 7/10/14; Fri 8/1/14. 27; 4.1; - Schedule lot stake-out; 1.00d; 13; Thu 7/10/14; Thu 7/10/14. 28; 4.2; - Stake lot; 1.00d; 27FS+3d; Wed 7/16/14; Wed 7/16/14. 29; 4.3; - File Grading Permit Application; 1.00d; 16; Thu 7/10/14; Thu 7/10/14. 30; 4.4; - File Building Permit Application; 3.00d; 14,15,16; Thu 7/10/14; Mon 7/14/14. 31; 4.5; - Post Lot Identification; 1.00d; 28,29,30; Thu 7/17/14; Thu 7/17/14. 32; 4.6; - Meet Sed. Control Insp.; 1.00d; 29FS+2d,28,31; Fri 7/18/14; Fri 7/18/14. 33; 4.7; - Walk Lot w/ Owner; 1.00d; 32; Mon 7/21/14; Mon 7/21/14. 34; 4.8; - Install Construction Entrance; 1.00d; 32,33; Tue 7/22/14; Tue 7/22/14. 35; 4.9; - Install Sediment Controls; 2.00d; 32,33; Tue 7/22/14; Wed 7/23/14. 36; 4.10; - Sediment Control Insp.; 1.00d; 34,35; Thu 7/24/14; Thu 7/24/14. 37; 4.11; - Grading Permit Issued; 1.00d; 36; Fri 7/25/14; Fri 7/25/14. 38; 4.12; - County Permit Process; 10.00d; 30; Tue 7/15/14; Mon 7/28/14. 39; 4.13; - Building Permit Approved; 1.00d; 38,37; Tue 7/29/14; Tue 7/29/14. 40; 4.14; - Pay Permit Fees and Excise Taxes; 1.00d; 39FS+2d; Fri 8/1/14; Fri 8/1/14. 41; 4.15; - Building Permit Issued; 0.00d; 40; Fri 8/1/14; Fri 8/1/14. 42; 5; Site Work; 7.00d; .; Mon 7/28/14; Tue 8/5/14. 43; 5.1; - Clear Lot; 3.00d; 37; Mon 7/28/14; Wed 7/30/14. 44; 5.2; - Strip Topsoil & Stockpile; 1.00d; 43; Thu 7/31/14; Thu 7/31/14. 45; 5.3; - Stake Lot for Excavation; 1.00d; 43; Thu 7/31/14; Thu 7/31/14. 46; 5.4; - Rough grade lot; 1.00d; 43,45; Fri 8/1/14; Fri 8/1/14. 47; 5.5; - Excavate for foundation; 2.00d; 39,45,43,46; Mon 8/4/14; Tue 8/5/14. 48; 6; Foundation; 24.00d; .; Wed 8/6/14; Mon 9/8/14. 49; 6.1; - Layout footings; 1.00d; 47; Wed 8/6/14; Wed 8/6/14. 50; 6.2; - Dig Footings & Install Reinforcing; 1.00d; 49; Thu 8/7/14; Thu 8/7/14. 51; 6.3; - Footing Inspection; 0.00d; 50; Thu 8/7/14; Thu 8/7/14. 52; 6.4; - Pour footings; 1.00d; 51; Fri 8/8/14; Fri 8/8/14. 53; 6.5; - Pin Footings; 1.00d; 52; Mon 8/11/14; Mon 8/11/14. 54; 6.6; - Stock Block, Mortar, Sand; 1.00d; 53; Tue 8/12/14; Tue 8/12/14. 55; 6.7; - Build Block Foundation; 15.00d; 53,54; Wed 8/13/14; Tue 9/2/14. 56; 6.8; - Foundation Certification; 0.00d; 55; Tue 9/2/14; Tue 9/2/14. 57; 6.9; - Draw #1 (Location Survey); 0.00d; 56; Tue 9/2/14; Tue 9/2/14. 58; 6.10; - Fill Block Cores w/ Concrete; 1.00d; 55; Wed 9/3/14; Wed 9/3/14. 59; 6.11; - Steel Delivery; 1.00d; 58; Thu 9/4/14; Thu 9/4/14. 60; 6.12; - Set Lintels, Bolts, Cap Block; 2.00d; 59; Fri 9/5/14; Mon 9/8/14. 61; 6.13; - Lumber Delivery; 1.00d; 58; Thu 9/4/14; Thu 9/4/14. 62; 6.14; - Waterproofing and Drain Tile; 1.00d; 61; Fri 9/5/14; Fri 9/5/14. 63; 7; Rough Carpentry; 44.00d; .; Tue 9/9/14; Fri 11/7/14. 64; 7.1; - Set Steel; 1.00d; 60; Tue 9/9/14; Tue 9/9/14. 65; 7.2; - 1st Floor Deck Framing; 4.00d; 64; Wed 9/10/14; Mon 9/15/14. 66; 7.3; - 1st Floor Wall Framing; 4.00d; 65; Tue 9/16/14; Fri 9/19/14. 67; 7.4; - Draw #2 (First Floor Deck); 0.00d; 66; Fri 9/19/14; Fri 9/19/14. 68; 7.5; - 2nd Floor Deck Framing; 2.00d; 67; Mon 9/22/14; Tue 9/23/14. 69; 7.6; - Draw #3 (Second Floor Deck); 0.00d; 68; Tue 9/23/14; Tue 9/23/14. 70; 7.7; - 2nd Floor Wall Framing; 3.00d; 69; Wed 9/24/14; Fri 9/26/14. 71; 7.8; - Set Roof Trusses; 2.00d; 70; Mon 9/29/14; Tue 9/30/14. 72; 7.9; - Frame Roof; 7.00d; 71; Wed 10/1/14; Thu 10/9/14. 73; 7.10; - Install Roof Plywood; 5.00d; 72; Fri 10/10/14; Thu 10/16/14. 74; 7.11; - Install Windows & Doors; 2.00d; 73,111; Wed 10/22/14; Thu 10/23/14. 75; 7.12; - Frame Basement; 3.00d; 72,81; Fri 10/10/14; Tue 10/14/14. 76; 7.13; - Frame Basement Bulkheads; 2.00d; 75,87,93; Thu 11/6/14; Fri 11/7/14. 77; 8; Concrete Slabs; 8.00d; .; Thu 9/18/14; Mon 9/29/14. 78; 8.1; - Basement Slab Preparation; 2.00d; 65,91; Thu 9/18/14; Fri 9/19/14. 79; 8.2; - Termite Treatment Basment Slab; 1.00d; 78; Mon 9/22/14; Mon 9/22/14. 80; 8.3; - Slab Inspection; 1.00d; 79; Tue 9/23/14; Tue 9/23/14. 81; 8.4; - Pour Basement Slab; 1.00d; 80; Wed 9/24/14; Wed 9/24/14. 82; 8.5; - Prep Garage Slab; 1.00d; 81; Thu 9/25/14; Thu 9/25/14. 83; 8.6; - Termite Treatment Garage Slab; 1.00d; 82; Fri 9/26/14; Fri 9/26/14. 84; 8.7; - Pour Garage Slab; 1.00d; 83; Mon 9/29/14; Mon 9/29/14. 85; 9; H.V.A.C.; 17.00d; .; Fri 10/10/14; Mon 11/3/14. 86; 9.1; - HVAC Layout & Measure; 1.00d; 72; Fri 10/10/14; Fri 10/10/14. 87; 9.2; - HVAC Rough-in; 5.00d; 86,111; Wed 10/22/14; Tue 10/28/14. 88; 9.3; - HVAC Set Indoor Units; 2.00d; 81,87; Wed 10/29/14; Thu 10/30/14. 89; 9.4; - HVAC Temporary Heat; 2.00d; 88; Fri 10/31/14; Mon 11/3/14. 90; 10; Plumbing Rough-in; 37.00d; .; Tue 9/16/14; Wed 11/5/14. 91; 10.1; - Plumbing Sub-slab; 2.00d; 65; Tue 9/16/14; Wed 9/17/14. 92; 10.2; - Plumbing Layout; 1.00d; 91,87; Wed 10/29/14; Wed 10/29/14. 93; 10.3; - Plumbing rough-in; 5.00d; 92; Thu 10/30/14; Wed 11/5/14. 94; 11; County Plumbing Sub-slab Inspection; 0.00d; 91; Wed 9/17/14; Wed 9/17/14. 95; 12; County Plumbing Rough-in Inspection; 0.00d; 93; Wed 11/5/14; Wed 11/5/14. 96; 13; Electric Rough-in; 19.00d; .; Fri 10/24/14; Wed 11/19/14. 97; 13.1; - Set Electric Boxes; 2.00d; 74; Fri 10/24/14; Mon 10/27/14. 98; 13.2; - Install Electric Service Panel; 2.00d; 97; Tue 10/28/14; Wed 10/29/14. 99; 13.3; - Electrical Walk-through; 1.00d; 98; Thu 10/30/14; Thu 10/30/14. 100; 13.4; - Electrical Rough-wire; 14.00d; 99; Fri 10/31/14; Wed 11/19/14. 101; 14; Specialty Rough-ins; 5.00d; .; Thu 11/20/14; Wed 11/26/14. 102; 14.1; - Central Vacuum Rough-in; 5.00d; 100; Thu 11/20/14; Wed 11/26/14. 103; 14.2; - Alarm System Rough-in; 5.00d; 100; Thu 11/20/14; Wed 11/26/14. 104; 14.3; - Telephone System Rough-in; 5.00d; 100; Thu 11/20/14; Wed 11/26/14. 105; 14.4; - Television System Rough-in; 5.00d; 100; Thu 11/20/14; Wed 11/26/14. 106; 14.5; - Audio Visual Rough-in; 5.00d; 100; Thu 11/20/14; Wed 11/26/14. 107; 15; County Electrical inspection; 0.00d; 96,101; Wed 11/26/14; Wed 11/26/14. 108; 16; Draw #5 (Rough-ins complete); 0.00d; 95,107; Wed 11/26/14; Wed 11/26/14. 109; 17; County Framing Inspection; 0.00d; 95FS+1d,107FS+1d; Thu 11/27/14; Thu 11/27/14. 110; 18; Roofing; 68.00d; .; Fri 10/17/14; Tue 1/20/15. 111; 18.1; - Roofing Paper Installed; 3.00d; 73; Fri 10/17/14; Tue 10/21/14. 112; 18.2; - Draw #4 (Roof, windows, doors); 0.00d; 74,111; Thu 10/23/14; Thu 10/23/14. 113; 18.3; - Stock Roof Shingles; 1.00d; 112; Fri 10/24/14; Fri 10/24/14. 114; 18.4; - Install Roof Shingles; 7.00d; 113,119; Mon 1/12/15; Tue 1/20/15. 115; 19; Exterior Finishes; 56.00d; .; Fri 10/24/14; Fri 1/9/15. 116; 19.1; - Siding; 3.00d; 74; Fri 10/24/14; Tue 10/28/14. 117; 19.2; - Exterior Trim; 7.00d; 116; Wed 10/29/14; Thu 11/6/14. 118; 19.3; - Brick Arch Forms; 1.00d; 117; Fri 11/7/14; Fri 11/7/14. 119; 19.4; - Brick Veneer; 45.00d; 118; Mon 11/10/14; Fri 1/9/15. 120; 20; Insulation; 5.00d; .; Fri 11/28/14; Thu 12/4/14. 121; 20.1; - Caulk & Air Seal; 1.00d; 109; Fri 11/28/14; Fri 11/28/14. 122; 20.2; - Draft & Fire Stop; 1.00d; 121; Mon 12/1/14; Mon 12/1/14. 123; 20.3; - Batt Insulation; 3.00d; 121,122; Tue 12/2/14; Thu 12/4/14. 124; 21; County Insulation Inspection; 0.00d; 123,120; Thu 12/4/14; Thu 12/4/14. 125; 22; BGE Energy Wise Inspection; 0.00d; 124; Thu 12/4/14; Thu 12/4/14. 126; 23; Drywall; 26.00d; .; Fri 12/5/14; Fri 1/9/15. 127; 23.1; - Stock Drywall; 1.00d; 124; Fri 12/5/14; Fri 12/5/14. 128; 23.2; - Hang Drywall; 5.00d; 127; Mon 12/8/14; Fri 12/12/14. 129; 23.3; - Remove Scrap Drywall; 1.00d; 128; Mon 12/15/14; Mon 12/15/14. 130; 23.4; - Tape and Finish Drywall; 15.00d; 128,129; Tue 12/16/14; Mon 1/5/15. 131; 23.5; - Sand Drywall; 1.00d; 130; Tue 1/6/15; Tue 1/6/15. 132; 23.6; - Drywall Point-up; 3.00d; 131; Wed 1/7/15; Fri 1/9/15. 133; 24; Draw #6 (Insulation & drywall applied); 0.00d; 128,126; Fri 1/9/15; Fri 1/9/15. 134; 25; Floor Finishes; 76.00d; .; Tue 1/13/15; Tue 4/28/15. 135; 25.1; - Ceramic Tile; 15.00d; 142; Tue 1/13/15; Mon 2/2/15. 136; 25.2; - Install Hardwood Floor; 4.00d; 146; Fri 3/27/15; Wed 4/1/15. 137; 25.3; - Sand, Stain, Seal Hardwood; 5.00d; 196; Thu 4/16/15; Wed 4/22/15. 138; 25.4; - Install Carpet; 4.00d; 137; Thu 4/23/15; Tue 4/28/15. 139; 25.5; - Final Coat Hardwood; 2.00d; 196; Thu 4/16/15; Fri 4/17/15. 140; 26; Paint; 59.00d; .; Wed 1/7/15; Mon 3/30/15. 141; 26.1; - Prep Drywall for Prime Coat; 2.00d; 131; Wed 1/7/15; Thu 1/8/15. 142; 26.2; - Prime Paint Drywall; 2.00d; 141; Fri 1/9/15; Mon 1/12/15. 143; 26.3; - Prep Trim for Prime Coat; 2.00d; 142,152; Wed 1/21/15; Thu 1/22/15. 144; 26.4; - Prime Trim; 2.00d; 143; Fri 1/23/15; Mon 1/26/15. 145; 26.5; - Finish Coat Trim; 10.00d; 144,156; Mon 2/23/15; Fri 3/6/15. 146; 26.6; - Finish Coat Drywall; 14.00d; 145,132; Mon 3/9/15; Thu 3/26/15. 147; 26.7; - Caulk Exterior Windows & Doors; 1.00d; 146,117; Fri 3/27/15; Fri 3/27/15. 148; 26.8; - Finish Coat Exterior Trim & Siding; 1.00d; 147; Mon 3/30/15; Mon 3/30/15. 149; 27; Draw #7 (Roofing, masonry, siding); 0.00d; 114,157; Tue 3/31/15; Tue 3/31/15. 150; 28; Interior Trim; 29.00d; .; Tue 1/13/15; Fri 2/20/15. 151; 28.1; - Interior Trim Delivery; 1.00d; 142; Tue 1/13/15; Tue 1/13/15. 152; 28.2; - Install Interior Doors; 5.00d; 151; Wed 1/14/15; Tue 1/20/15. 153; 28.3; - Install Interior Trim; 15.00d; 152; Wed 1/21/15; Tue 2/10/15. 154; 28.4; - Install Cabinetry; 5.00d; 153; Wed 2/11/15; Tue 2/17/15. 155; 28.5; - Install Appliances; 1.00d; 154; Wed 2/18/15; Wed 2/18/15. 156; 28.6; - 1st Punch-out Interior Trim; 2.00d; 155,144; Thu 2/19/15; Fri 2/20/15. 157; 29; H.V.A.C. Trim; 1.00d; 140; Tue 3/31/15; Tue 3/31/15. 158; 29.1; - Install Grills & Registers for Paint; 1.00d; 131; Tue 3/31/15; Tue 3/31/15. 159; 29.2; - Set Outdoor Units; 1.00d; 165; Tue 3/31/15; Tue 3/31/15. 160; 30; Plumbing Trim; 5.00d; .; Thu 4/2/15; Wed 4/8/15. 161; 30.1; - Set Fixtures; 4.00d; 135,136,146,154; Thu 4/2/15; Tue 4/7/15. 162; 30.2; - Connect Appliances; 1.00d; 161; Wed 4/8/15; Wed 4/8/15. 163; 31; County Final Plumbing Inspection; 0.00d; 160; Wed 4/8/15; Wed 4/8/15. 164; 32; Exterior Landscaping; 32.00d; .; Mon 1/12/15; Tue 2/24/15. 165; 32.1; - Rough Final Grade; 1.00d; 119; Mon 1/12/15; Mon 1/12/15. 166; 32.2; - Patios; 7.00d; 165,119; Tue 1/13/15; Wed 1/21/15. 167; 32.3; - Porches; 5.00d; 166,119; Thu 1/22/15; Wed 1/28/15. 168; 32.4; - Sidewalks; 7.00d; 167,119; Thu 1/29/15; Fri 2/6/15. 169; 32.5; - Decks; 7.00d; 168,119; Mon 2/9/15; Tue 2/17/15. 170; 32.6; - Driveways; 2.00d; 165,169; Wed 2/18/15; Thu 2/19/15. 171; 32.7; - Final Grade and Seed; 3.00d; 170,166,167,168; Fri 2/20/15; Tue 2/24/15. 172; 33; Electrical Final Trim; 160.00d; .; Tue 6/5/14; Wed 1/14/15. 173; 33.1; - Switch & Plug; 2.00d; 142,100; Tue 1/13/15; Wed 1/14/15. 174; 33.2; - Install Fixtures; 1.00d; 146; Thu 3/27/15; Thu 3/27/15. 175; 33.3; - Connect Appliances; 1.00d; 155,162; Thu 4/9/15; Thu 4/10/15. 176; 34; Hardware; 12.00d; .; Fri 3/27/15; Mon 4/13/15. 177; 34.1; - Door Hardware; 2.00d; 145,146; Fri 3/27/15; Mon 3/30/15. 178; 34.2; - Bath Hardware; 2.00d; 145,146; Fri 3/27/15; Mon 3/30/15. 179; 34.3; - Mirrors; 5.00d; 178; Tue 3/31/15; Mon 4/6/15. 180; 34.4; - Shower Doors; 10.00d; 178; Tue 3/31/15; Mon 4/13/15. 181; 35; Draw #8 (Prime paint, cabinets, doors); 0.00d; 142,152,154; Tue 2/17/15; Tue 2/17/15. 182; 36; Draw #9 (Trim, furnace, hrdwd, tile, rails); 0.00d; 153,181; Tue 2/17/15; Tue 2/17/15. 183; 37; Draw #10 (Plumbing & elec. trim, final paint); 0.00d; 146,182; Thu 3/26/15; Thu 3/26/15. 184; 38; Final Building Inspection; 0.00d; 183; Thu 3/26/15; Thu 3/26/15. 185; 39; Use & Occupancy Certificate; 0.00d; 184FS+3d; Tue 3/31/15; Tue 3/31/15. 186; 40; First Walk-thru; 0.00d; 185; Tue 3/31/15; Tue 3/31/15. 187; 41; Draw #11 (Final payment per contract); 0.00d; 186; Tue 3/31/15; Tue 3/31/15. 188; 42; Final Punch-out; 9.00d; .; Wed 4/1/15; Mon 4/13/15. 189; 42.1; - Punch Out Walk-thru List; 4.00d; 186; Wed 4/1/15; Mon 4/6/15. 190; 42.2; - Trim and Adjust Doors; 2.00d; 184,189; Tue 4/7/15; Wed 4/8/15. 191; 42.3; - Paint Touch-up; 3.00d; 190; Thu 4/9/15; Mon 4/13/15. 192; 43; Cleaning; 14.00d; .; Fri 3/27/15; Wed 4/15/15. 193; 43.1; - Windows; 3.00d; 145,146; Fri 3/27/15; Tue 3/31/15. 194; 43.2; - Rough Clean; 3.00d; 193; Wed 4/1/15; Fri 4/3/15. 195; 43.3; - Final Clean; 2.00d; 176,188; Tue 4/14/15; Wed 4/15/15. 196; 44; Final Walk-through; 0.00d; 187,188,192; Wed 4/15/15; Wed 4/15/15. 197; 45; Move-in; 0.00d; 196FS+1d; Thu 4/16/15; Thu 4/16/15. |
| --- | --- |